## To do
To Do |  | 14/28 completed
✓ | Date | Task | Assigned to | Notes
Starting Up
TRUE | 2023-08-24 | Setup your own page in the list of projects
TRUE | 2023-08-30 | Created a Github space for the repository (MIT license) |  | There is a GitHub set up and added to the page in Canvas. I havent added anyone to it
FALSE | 2023-08-30 | Is Dr. Jamieson (drpaj12) added as contributor (what about your other advisors)?
TRUE | 2023-08-30 | Started a report on Google Docs so you can add citations and documentation as you go
TRUE | 2023-08-31 | Made agreement with each other on who and what is expected of the group members
TRUE | 2023-08-28 | Set a time to meet with Dr. Jamieson (and other Advisor) weekly
TRUE | 2023-09-02 | Set or find a time to work together on the project (min. 2 hrs a week)
TRUE | 2023-08-28 | Have contact info for each member (phone, email)
TRUE | 2023-08-30 | Todo list creation with name allocation (electronic) or means to manage your project
Research
TRUE | 2023-09-05 | Read Papers | All
TRUE | 2023-09-05 | Research what language creating a simulation application would be easiest in | All | Current options: Python - pyspice, this works with LTSpice which we obviously discussed was too detailed for our needs. Xyce utilizes c++ in the background and is utilized for large scale parallel computing projects, I also found a paper about simulating neural network systems with it which could be very useful.
TRUE |  | Research circuit analysis/ buck converter, theoretical stuff | Ethan
TRUE |  | Research sensors/ buck converter, microcontroller interaction with sensors, microcontroller algorithm | Jimmy
TRUE |  | Research how to create simulator | Alecea
FALSE
FALSE
FALSE
What are we doing
TRUE |  | Can you concisely describe the problem in 2 minutes to an engineer? a layperson? your family members?
FALSE |  | Can we write a 1-paragraph description of what we are doing? This should start your report and GitHub wiki description.
FALSE | 2023-09-05 | Do we have a rough plan of where we are going next? | All
FALSE | 2023-09-05 | Make a decision on if we want to use pre-made simulator or not | All
FALSE |  | Attempt to figure out why certain variables are applicable mathmatically to correlate to power failure
FALSE
FALSE
FALSE
FALSE
FALSE
Report
FALSE |  | Included a section on alternative designs and decisions you made to pick your current design
FALSE |  | Ethical considerations of the design/solution/product you have created
FALSE |  | Citations to referenced material (not your ideas)
FALSE |  | Have you completed your reflexive essay?
FALSE |  | Have you filled out YOUR peer evaluation?
FALSE |  | Have you submitted it? To ECE 448/449 course and a version is on Canvas
FALSE
FALSE
Deliverables
FALSE |  | Is code licensed MIT and organized well?
FALSE |  | Is there documentation (READMEs, HOW TO BUILD, COMMENTS, WIKI, etc.)?
FALSE |  | Is there a video(s) showing tool(s) builds
FALSE
FALSE
FALSE
Presentation
TRUE |  | Have we done a dry run with our advisor?
TRUE |  | Have we created the slides…are they excessively wordy?
TRUE |  | Have we created an accompanying handout so our slides aren’t wordy?
TRUE |  | Do we have a demo at this point? If yes, do we have a backup video of the demo working?
TRUE |  | Will we be dressing up?
TRUE |  | Have we sent our slide deck post presentation to advisors and stored on this canvas site?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Poster
FALSE |  | Have we checked this with advisors?
FALSE |  | Have we sent it to the printer?
FALSE |  | Do we have a demo? Do we have video backups?
FALSE |  | Do we have a handout for people coming by that provides more details?
FALSE |  | Have we sent our poster electronic files post printing to and stored it on this canvas site?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE |  | ESR triangulates the wave
FALSE |  | define what makes a capacitor worse and simulate it - Increase ESR and Capacitance decreases - when capacitor fails
FALSE |  | degrade capacitor and examine results
FALSE |  | figure out how to model things to make it more accurate
FALSE |  | discuss what we want to do in the furture in terms of real world virtual twin modeling
FALSE |  | Texas instrument microcontrollers - suggestions for microcontrollers to gather data from the buck converter vc and il
FALSE |  | other group got ADC to get digita values - (we would need one)
FALSE
FALSE
FALSE